## Main
Resale Bidding Website Launching Plan
SL | Launch | Activity | Details | Date | Budget
1 | Pre-soft launch Activity | Create FB page & Community Forums (Facebook Group) | Create Facebook page and Community Group | 2024-01-14 | -
3 |  | Design finalization | Logo, Profile Picture, Cover Photo, Page Post | 2024-01-16 | -
4 |  | Social Media Advertising and posting Click Here for Launching Event of Social Media Budget | We will be posting multiple pre-post regarding the launching and also run some ads regarding the event as well, to create vibe and awareness | 16/1/2024 -22/1/2024 | 13225
5 | Soft Launch | Website promo (teaser) | Video presentation the Website | 2024-01-16 | -
6 |  | Tutorial for website | Video that will show how sign in, how to bid and how to sign out | 2024-01-15
7 |  | Soft Launch by MD Madam | MD Madam will reveal the portal for our employees (Will be done via StreamYard) | 2024-01-17 | 13092.75
8 | Pre-launch Activity | SEO Optimization for Local Searches | Facebook Pixel, Google Tag Manager, Google Analytics | 17/1/24 (depends on IT Department availability as well) | -
9 |  | Implementing Google Tag and Pixel in website |  | 17/1/24 (depends on IT Department availability as well) | -
10 |  | Website Kit for TG | Leaflet (2,000 pcs) | 20/1/24 | 6000
11 | During Launching | Physical Launching at Mela |  | 23/1/24
12 |  | Branding elements at mela | Backdrop, X-banner (4), QR code table top (1), dedicated sticker (as per car available), Facebook Post cutout (1), Facebook Cover Cutout (1), Decoration Item, T-shirt (100 pcs) | 23/1/24 | 84000
13 |  | Social Media Advertising and posting Click Here for Launching Event of Social Media Budget | We will do live streaming and some posting during the day of event | 23/1/2024 | 6612.5
14 |  | Live-streaming | We will be doing online event streaming with the same Streamyard subscription and will be assisted by third-party | 23/1/24 & for any big events | 20000
15 | Post Launching | Post Launching Promo (for YouTube & Facebook) | Promo about how/why to use the website | 23/1/24 & any other event | -
16 |  | Influencer Marketing & Vlogging | MRK Analysis | 22/1/24 | 10000
17 |  | User Testimonials and Success Stories | We will shoot Testimonials and Success Stories and post it in social media | 23/2/24 | -
18 |  | Portal Reviews and Comparisons | We will post static picture containing reviews of the users | Depending on the vlogger publishing the video | -
19 |  | Social Media Advertising Click Here for Launching Event of Social Media Budget | We will be conducting Post social media activities | From 23/1/24, & will continue depending on the budget allocated | 26450
20 |  | Email Campaigns | We will send emails to potential buyers containing information regarding the website | 23/1/24 & every month one mailer | -
21 |  | SMS Marketing | We will SMS to potential buyers containing information regarding the website | 23/1/24 & for any big events | 6000
22 |  | PR Campaign National: Newspaper 03 - 04, 06 - 08 Online Divisional 7 District: Newspaper & Online 02 - 03 | We will circulate news in local newspaper and online news portal | 24/1/24 | 120000
23 |  | Facebook Shops | Will be trying to showcase the website products in Facebook shop (if possible) | Will be based on experimental basis | -
Total |  |  |  |  | 305380.25

## Digital Marketing Plan
Resale Bidding Website Digital Marketing Launching Plan
Date | Day | Event | Post type | Ad Objective | Ad cost
2024-01-15 | Monday | Something new is coming | Static | Awareness/Engagement | 20
2024-01-16 | Tuesday | Bringing something special for it's customer | Staic/Video | Awareness/Engagement | 20
2024-01-17 | Wednesday | Only 6 days left post | Static | Awareness/Engagement | 20
2024-01-18 | Thursday | Engagment post about what cold be coming | Static | Awareness/Engagement
2024-01-19 | Friday | Only 4 days left post | Static | Awareness/Engagement | 10
2024-01-20 | Saturday | - | - | - | -
2024-01-21 | Sunday | Half Logo Reveal | Staic/Video | Awareness/Engagement | 20
2024-01-22 | Monday | Only 1 days left post | Static | Awareness/Engagement | 10
2024-01-23 | Tuesday | Big Reveal | Live session/Email/SMS |  | 50
2024-01-24 | Wednesday | Website promo | Staic/Video | Awareness/Engagement | 50
2024-01-25 | Thursday | Benefit of using the website | Static | Lead | 50
2024-01-26 | Friday | Event Picture Boosting | Static | Awareness/Engagement | 25
2024-01-27 | Saturday | - | - | - | -
2024-01-28 | Sunday | Event Teaser | Static | Awareness/Engagement | 25
2024-01-29 | Monday | How to use the website (static post) | Static | Lead | 25
2024-01-30 | Tuesday | Tips and Tricks for the website | Static | Lead | 25
|  |  |  | Total (Dollar) | 350
|  |  |  | Total BDT | 46287.5

## Branding elements
Resale Bidding Website Branding elements at mela
Name | Quantity | Details | Budget
Leaflet | 2,000 pcs | Leaflet will be printed to be distributed during the mela and also for future usage | 6000
Backdrop | 1 | One backdrop will be used for stall display | 12000
X-banner | 4 | 4 backdrop will be used for advertising display | 4000
QR code table tent | 1 | One QR Code Table tent will be used for customers scanning the code and directed to the website directly | 2000
Dedicated sticker | As per car availability | A decicated QR code sticker will be displayed for all the cars displayed, and upon scanning the QR Code customer will be directed to the page. | -
Facebook frame cutout | 1 | One facebook post cutout can be used for customers engagement with the facebook page inforamtion | 5000
Facebook Cover photo booth | 1 | One Facebook cover photo cutout can be used for customers group engagement with the Facebook page information | 20000
Decoration Cost | As per needed | Table, Chair, Carpet etc | 20000
Branded T-shirt | 100 pcs | T-shirt will have QR code in the back and the brand logo in the front | 15000
| Total |  | 84000